## Sheet1
Equality Action Plan 2019-21
Key | Included in SDS Operational Plan
Outcome | 2019-2020 Targets | 2019-2020 Progress | 2020-21 Targets | 2020-2021 Progress | Responsibility
Equality Standard Progress | Organisational audit | Complete |  |  | Opportunities & Equalities Manager
| TNA staff and board | Audit completed with staff and board |  |  | Opportunities & Equalities Manager
| TNA - additional TNA specific to characteristics | Audit completed with staff and board - JB to analyse
| Set up appropriate training from the gaps in TNA | Evidence gathered - analysis to be done | Staff/board training calendar established from TNA
| GAP Analysis | Started at staff away days in June but more to be done | Complete GAP Analysis |  | CEO/Coach Education & Learning Manager/Opportunities & Equalities Manager
| Establish a new Equality Action Plan | Complete |  |  | All staff
| Identify a new Equality Champion on the SDS Board | Complete |  |  | SDS Board/CEO
Reflective Report | Outline reflective report format | Draft structure produced |  |  | CEO/Opportunities & Equalities Manager
Equality Impact Assessments | Complete Equality Impact Assessments in line with Board Review Cycle | Part of Board Policy Review Cycle |  |  | Staff member with responsibility to complete for ratification by Board
Completed policies 2018/20: Risk Management Policy, Complaints Handling Policy, Safeguarding Policies & Procedures
|  | 9 other policies considered but not applicable for EIA | To be completed in 2020: Equality Policy, Fraud Policy, Privacy & Data Protection Policy, Classification Policy, Communications Policy, Social Media Policy, Recruitment and Selection Policy, Anti-Harassment & Bullying Policy, Recruitment documents and contracts, Board Recruitment & Procedures, Anti-Doping Policy
7 other policies considered but not applicable for EIA
Equality training, support and development | Staff/Board to complete TNA | Complete
| Work in partnership with SGBs to support 10 mainstream sports clubs to provide inclusion training | SDS worked with 24 SGBs in 2019 to deliver UK Disability Inclusion Training, in depth work with Scottish Target Shooting, Scottish Archery Association, Scottish Swimming, Scottish Athletics, Scottish Taekwondo, Scottish Karate Governing Body, Scottish Motor Sports, Scottish Canoe Association, Boccia, Scottish Rugby Union | Work with 6 SGBs to support sports clubs to provide inclusion training: Scottish Swimming, Scottish Athletics, Scottish Canoe Association, Scottish Target Shooting, Scottish Rugby Union, Scottish Taekwondo |  | Coach Education & Development Manager/Administrators/SDS tutors
| Deliver an annual education and development programme in partnership with national, regional and local partners to develop the workforce. | On going - SDS was asked by SQA to be part of the HNC and HND review of qualifications. The AIM and STEP models have been embedded in both the HNC and HND. SDS is part of the national quality design team that is responsible for evolving SGB qualifications to ensure quality. | Training delivered to all colleges through SQA. | Date established, postponed due to Covid-19. SQA are using training as part of the EIA. | Coach Education & Development Manager/Administrators/SDS tutors
| Accessibility to qualifications and courses for coaches with a disability | On going - Big Lottery funded Young Start programme. Young Start Programme supported 20 young coaches with disabilities to gain qualifications. | Big Lottery funding applied for new cohort of Young Start Programme to support potential coaches with a disability.
Increase the number of inactive to active participants | Get Out Get Active Programme delivered in 2016-2019 focussing on inactive to active, active together, enhancing existing provision and sustainability | 3 branches were involved as localities in the programme to produce evidence of people with a disability becoming active (separate report) | GOGA 2 Health based programme to operate in Tayside from 2020-2023
GOGA 2 Manager Tayside appointed April 2020
Increase the number of women and girls involved in disability sport | Boccia development officer recruited (specifically for women and girls) | Officer in place since June 2019 - April 2020. Recruited 4 new boccia players and case study completed for sportscotland. | Recruit Boccia Development Officer with the focus on Women and Girls continuing. |  | Performance Manager/Boccia Development Officer
Increase females accessing Boccia Clubs.
| Branch specific case studies of good practice | Forth Valley Disability Sport presented at GOGA conference UK in 2019 on women and girls programme | Branches continue to develop and share case studies and good practice. | GOGA presentation on learnings at the SDS Branch Conference 2020 | GOGA Manager/All staff
|  |  | Share specific case studies/videos on women and girls and examples of integrated sessions with disabled and non-disabled athletes. |  | GOGA Manager/All staff
| Increase the number of females participating in SDS Nation Events | Stats provided in separate report |  |  | Opportunities & Events Manager
Increase the number of people with severe and complex disabilities participating in sport | Deliver specific come and try days for impairment groups | Delivered amputee come and try day, Wheels to Water, in 2019 | Deliver specific come and try days for impairment groups | Wheels to Water postponed until September in 2020 due to Covid-19. Wheelchair Extravaganza due to take place in September 2020. | Staff with specific sport responsibilities.
| Severe and complex training | Bespoke course developed - 1 delivered and one postponed | Severe and complex training |  | Coach Education & Development Manager
| SDS 3 day summer camp held for participants with physical and sensory disabilities | 36 participants in 2019 - a high number had severe and complex needs. Most attendees were identified through regional programmes. | SDS 3 day summer camp scheduled for participants with physical and sensory disabilities |  | Opportunities & Events Manager
| A minimum of 5 Regional para sport days | 4 para sport days (West, Grampian, Central, Tayside). East Parasport cancelled due to Covid-19 and will be rescheduled. Those held in 2019 - 345 pupils attended para sport days from 19 mainstream schools 97 (13%) of individuals were supported by SDS to transition into weekly activities. | A minimum of 5 Regional para sport days | 18 Sept - Grampian 26 Sept - Highland 28 Sept - Central March 2021 - West, Tayside and East 1 additional parasport day to be held in 2020 in Highland | Pathways Manager and Regional Development Managers
| 10% increase in participation levels from athletes and players with a physical and/or sensory impairment in SDS events programme | Stats provided in separate report | 10% increase in participation levels from athletes and players with a physical and/or sensory impairment in SDS events programme |  | Opportunities & Events Manager
Increase the number of people with sensory disabilities taking part in sport | Agreed to hold Visual Impairment Day on a regional basis | Visual impairment day held in East in 2019 | Visual Impairment Day held in another region in 2020/21 |  | Pathways Manager
| Visual Impairment Group meeting every 6 months | Group met twice in 2019 | Visual Impairment Group meeting every 6 months |  | Pathways Manager
| Involvement in Inspiring Sport Programme | Goalball training delivered in Tayside and session set up in the west of Scotland. Football sessions also delivered through Celtic FC Foundation. | Dependant on funding. |  | CEO
| Deliver Visual Impairment Training | Training delivered in partnership with RNIB and Guide Dogs Scotland | Deliver Visual Impairment Training at University of Edinburgh in September |  | Coach Education & Development Manager
| 10% increase in participation levels from athletes and players with a physical and/or sensory impairment in SDS events programme | Statistics provided in separate report | 10% increase in participation levels from athletes and players with a physical and/or sensory impairment in SDS events programme |  | Opportunities & Events Manager
Increase number of people from a Black and ethnic minority group participating in disability sport | Identify and engage with BME groups | No progress | Set up a meeting with BEMIS/other appropriate groups in 2020/21 |  | Opportunities & Equalities Manager and CEO